## Tasks
No. |  | Start | Duration | Requires
Phase: Feasibility Study
A | Technology | 2025-06-23 | 1
B | Economics |  | 2 | A
C | Organization |  | 3 | B
Phase: Planning
D | Staff planning |  | 2 | C
E | Time planning |  | 2 | None
Phase: Design
F | Architecture + Storage |  | 4 | D,E
G | UX/UI |  | 5 | D,E
H | Prototype |  | 1 | F,G
I | Pitching |  | 2 | F,G,H

## Gantt
Tasks