## Tasks
No. |  | Start | Duration | Requires |  |  | June | [7 empty] | July
| Phase: Feasibility Study | [5 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | Technology | 2026-06-23 | 1 | bar: June 23
B | Economics |  | 2 | A | bar: June 24 to June 25
C | Organization |  | 3 | B | bar: June 26 to June 28
Phase: Planning
D | Staff planning |  | 2 | C | bar: June 29 to June 30
E | Time planning |  | 2 | None | bar: June 23 to June 24
Phase: Design
F | Architecture + Storage |  | 4 | D,E | bar: July 1 to July 4
G | UX/UI |  | 5 | D,E | bar: July 1 to July 5
H | Prototype |  | 1 | F,G | bar: July 6
I | Pitching |  | 2 | F,G,H | bar: July 7 to July 8
[5 empty] | Days | 16 | bar: June 23 to July 8
[5 empty] | Staffs | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
[5 empty] | Last day | 2026-07-08

## Gantt
Tasks